## Introduction
Network Development Report Datasheets 2024
Summary Page
Published April 2024
This document is the excel format version of the Network Development Report (NDR). The purpose of the NDR is to transparently communicate our investment decisions and future network intervention plans to stakeholders, and to highlight areas where Flexibility Services may be required. This benefits our stakeholders by enabling them to factor our network plans and requirements for Flexibility Services into their planning. This NDR uses a template that groups network development requirements according to the Grid Supply Point (GSP) that they are supplied by. This approach ensures that the data is presented consistently, aiding our stakeholders. As this report does not cover network constraints at GSPs which are National Grid assets, works on our network that have associated works at GSPs are listed in Table 1 but in the 'capacity added' column we have populated - GSP* along with a note stating that '*we are not reporting changes to Natianal Grid capacity'. Please note that in Table 1, asset interventions to be delivered in the years 2024 -to- 2028 have actual expected works start and completion years, while those to be delivered between 2029 -to- 2033 all have expected works start year of 2029 and completion year of 2033 as an indicative timeframe because the actual timelines are under review.
Contents
Worksheet |  | Description
Table 1 |  | Our planned network interventions over the next 10 years for our whole network down to the primary substation level
Table 2 |  | Our upcoming Flexibility Services requirements for future load driven capacity needs in the next 1-10 years
DOCUMENT CONTROL
Approvals
Role | Approver | Date
Author | Dr Richard Mandeya | 2024-04-26
Reviewer | Dr Neal Wade | 2024-04-29
Manager Approval | Dr Gillian Williamson | 2024-04-29
Version Control
Version | Comment | Date
V1.0 | First issue for Stakeholder Consultation | 2024-03-28
V1.1 | Second issue final publication | 2024-04-29

## Table 1
Licence Area | Northern Powergrid Operational Region | Grid Supply Point | GSP Postcode | Number of BSPs at GSP | Number of Primary Substations at GSP | Number of Customers at GSP | Supply Point/Primary/Circuit | Supply Point/Primary Substation Postcode | Planned Intervention | Driver | Expected start date | Expected completion date | Existing Rating (MVA) | New Rating (MVA) | Capacity Added (MVA)
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Denwick 66/20kV | NE66 3RG | Replacement of 20kV circuit breakers | Condition | Q1 2025 | Q4 2025 | 30 | 30 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Linton - Denwick 1 & 2 66kV Circuit | NE61 5DA | Replacement of 23km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Linton - Denwick No.2 66kV Circuit | NE61 3AX | Replacement of 1.2km of 66kV underground cables | Condition | Q2 2024 | Q4 2024 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Linton 66/20kV | NE61 3AX | Replacement of Transformer | Condition | Q2 2027 | Q3 2027 | 28 | 28 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Linton 66/20kV | NE61 3AX | Replacement of 20kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 5 | 33000 | Warkworth 66/20kV | NE65 0YD | Replacement of Transformer | Condition | Q1 2026 | Q3 2026 | 25 | 40 | 15
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Ashington 66/11kV | NE63 8UJ | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Bedlington Sw 66/20kV | NE22 5DN | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Benton Square 66/11kV | NE12 9SR | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | BLYTH - BEDLINGTON SW 1 (DUAL CIRCUIT) 66kV Circuit | NE24 1QP | Replacement of 0.7km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | BLYTH - BEDLINGTON SW 2 (DUAL CIRCUIT) 66kV Circuit | NE24 1QP | Replacement of 0.7km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Maddison Street 66/11kV | NE24 1DX | Replacement of 66/11kV transformer T2 and 66kV circuit breaker | Condition | Q4 2024 | Q3 2025 | 22.8 | 22.8 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Morpeth 66/20kV | NE61 6JT | Replacement of Switchgear | Condition | Q1 2026 | Q3 2026 | 28 | 30 | 2
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Reservoir 66/20kV | NE22 5QP | Replacement of 20kV switchgear in a new switchroom | Condition | Q1 2024 | Q2 2025 | 30 | 30 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/66kV | NE22 7BF | 1 | 12 | 112000 | Seaton Burn 66/20kV | NE13 6BH | Replacement of 66 & 20kV switchgear | Condition | Q1 2021 | Q4 2024 | 25 | 25 | 0
Northeast | Teeside | Hartmoor 275/66kV | TS27 3BL | 1 | 6 | 53000 | Hartmoor 275/66kV 66/20kV | TS27 3BL | Replacement of 66kV Transformer T2 | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Hartmoor 275/66kV | TS27 3BL | 1 | 6 | 53000 | Hartmoor 275/66kV 66/20kV | TS27 3BL | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Hartmoor 275/66kV | TS27 3BL | 1 | 6 | 53000 | Peterlee West 66/11kV | DH6 2RA | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Hawthorn Pit 66/20kV | DH6 2RX | Replacement of 20kV switchgear | Condition | Q1 2025 | Q4 2025 | 27.3 | 28 | 0.7
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Hawthorn Pit Grid 275/66kV | DH6 2TX | Replacement of 66kV circuit breakers | Condition | Q1 2024 | Q4 2024 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | HERRINGTON BURN - Hawthorn Pit Grid 275/66kV TEED 66kV Circuit | DH4 7AG | Replacement of 0.6km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Herrington Burn 66kV Switching Station | DH4 7AG | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Seaham 66/20kV | SR7 0PU | Construction of new 66/20kV primary substation | Load | Q3 2024 | Q3 2026 | 0 | 30 | 30
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Stoney Cut 66/20kV | SR7 8RQ | Replacement of 20kV switchgear | Condition | Q3 2023 | Q3 2024 | 31.8 | 31.8 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70000 | Tunstall 66/11kV | SR3 2NN | Replacement of 66kV circuit breaker | Condition | Q1 2024 | Q2 2024 | 30.5 | 30.5 | 0
Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82000 | HARROGATE - OATLANDS 1 & 2 33kV Circuit | HG1 2LA | Replacement of 8.6km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82000 | Harrogate - Starbeck 1 & 2 33kV Circuit | HG1 2LA | Replacement of 9.1km of 33kV underground cables | Condition | Q1 2024 | Q4 2024 |  |  | 0
Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82000 | Oatlands 33/11kV | HG2 8BY | Replacement of 11kV circuit breakers | Condition | Q1 2025 | Q1 2026 | 22.9 | 22.9 | 0
Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82000 | Ripon 33/11kV | HG4 1RA | Full substation upgrade including transformers, switchboards and incoming circuits | Load | Q3 2025 | Q4 2026 | 18.7 | 40 | 21.3
Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82000 | Wormald Green - Harrogate 1 &2 132kV Circuit | HG3 3PS | Replacement of 8km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Lackenby 275/66kV | TS6 7QR | 1 | 6 | 99000 | Guisborough 66/11kV | TS14 6GQ | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Lackenby 275/66kV | TS6 7QR | 1 | 6 | 99000 | Lackenby 275/66kV - Guisborough Feeder 2 66kV Circuit | TS6 7QR | Replacement of 0.9km of 66kV underground cables | Condition | Q1 2024 | Q3 2024 |  |  | 0
Northeast | Teeside | Lackenby 275/66kV | TS6 7QR | 1 | 6 | 99000 | Lackenby 275/66kV - Prissick 2 66kV Circuit | TS6 7QR | Replacement of 1km of 66kV underground cables | Condition | Q2 2025 | Q3 2025 |  |  | 0
Northeast | Teeside | Lackenby 275/66kV | TS6 7QR | 1 | 6 | 99000 | Spencerbeck 66/11kV | TS3 8TE | Replacement of 66kV circuit breakers | Condition | Q1 2026 | Q3 2026 | 38.1 | 38.1 | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Billingham Marsh House 33/11kV | TS23 2AS | Replacement 11kV switchgear | Fault level | Q1 2026 | Q3 2026 | 24 | 24 | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | BOWESFIELD – STOKESLEY 33kV Circuit | TS18 3HP | Replacement of 12km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | BOWESFIELD - URLAY NOOK 1 33kV Circuit | TS18 3HP | Replacement of 3.1km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | BOWESFIELD - URLAY NOOK 1,2,3 33kV Circuit | TS18 3HP | Replacement of 6.2km of 33kV underground cables | Condition | Q2 2023 | Q3 2025 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | BOWESFIELD - URLAY NOOK 2 33kV Circuit | TS18 3HP | Replacement of 3km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Darlington West 33/11kV | DL3 9QG | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Faraday Street 66/11kV | TS1 4JG | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Heighington 33/11kV | DL5 6SH | Replacement of Switchgear | Fault level | Q1 2026 | Q2 2026 | 27.4 | 27.4 | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | LEEMING BAR - CATTERICK CAMP 2 33kV Circuit | DL7 0RL | Replacement of 13.4km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Leeming Bar_Skeeby 132/33kV | DL7 0RP | Replacement of 11kV switchgear | Connections | Q1 2025 | Q3 2025 | 141 | 141 | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Malleable 66/11kV | TS18 2NR | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Millbank Lane 33/11kV | TS17 0AX | Replacement of Switchgear | Fault level | Q4 2025 | Q3 2026 | 21.1 | 21.1 | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | North Tees - Seal Sands No 1 & 2 132kV Circuit | TS23 1PX | Replacement of 0.6km of 132kV underground cables | Condition | Q1 2024 | Q3 2024 |  |  | 0
Northeast | Teeside | Norton 275/132kV | TS21 1EG | 10 | 34 | 246000 | Northallerton 33/11kV | DL7 0QE | Replacement of 33kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Offerton 275/33kV | SR4 9NR | 1 | 3 | 38000 | Mount Road 33/11kV | SR4 7LJ | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Offerton 275/33kV | SR4 9NR | 1 | 3 | 38000 | Offerton 275/33kV | SR4 9NR | replacement of 33kV switchboard | Connections | Q3 2027 | Q4 2028 |  |  | 1
Northeast | Northumberland, County Durham and Tyne & Wear | Offerton 275/33kV | SR4 9NR | 1 | 3 | 38000 | Pallion Trading 33/11kV | SR4 6SN | Replacement of 33kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Offerton 275/33kV | SR4 9NR | 1 | 3 | 38000 | Pallion Trading 33/11kV | SR4 6SN | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | North Yorkshire | Osbaldwick 400/132kV | YO10 3WA | 6 | 23 | 161000 | Eastfield 33/11kV | YO11 3NF | Replacement of Switchgear | Fault level | Q1 2027 | Q2 2027 | 32 | 32 | 0
Northeast | North Yorkshire | Osbaldwick 400/132kV | YO10 3WA | 6 | 23 | 161000 | Osbaldwick 400/132kV | YO10 3WA | Create a new 132kV GIS compound | Connections | Q2 2025 | Q3 2026 |  |  | 0
Northeast | North Yorkshire | Osbaldwick 400/132kV | YO10 3WA | 6 | 23 | 161000 | SCARBOROUGH GRID - NORTH STREET 2 33kV Circuit | YO11 2YH | Replacement of 2.4km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | North Yorkshire | Poppleton 275/33kV | YO26 6GB | 1 | 4 | 27000 | Poppleton 275/33kV | YO26 6GB | replacement of 33kV switchboard | Connections | Q1 2028 | Q4 2028 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | South Shields 275/33kV | NE34 9BT | 1 | 4 | 38000 | Garwood Street 33/11kV | NE33 5AG | Replacement of Switchgear | Fault level | Q4 2025 | Q3 2026 | 32 | 32 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | South Shields 275/33kV | NE34 9BT | 1 | 4 | 38000 | Jarrow 33/11kV | NE32 5LD | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | BELMONT - SPENNYMOOR 66kV Circuit | DH1 2HL | Replacement of 1.1km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | Belmont 66/11kV | DH1 2HN | Replacement of 66kV circuit breakers | Condition | Q1 2025 | Q3 2025 | 32 | 32 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | Durham East 66/11kV | DH1 5SU | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | Fishburn 66/20kV | TS29 6JN | Asset replacement | Condition | Q1 2026 | Q3 2026 | 28 | 28 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | Fylands Bridge 66/11kV | DL14 9TA | Replacement of 20kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | POTTER HOUSE - BELMONT 1 TEED 66kV Circuit | DH1 5FF | Replacement of 1.9km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | POTTER HOUSE - BELMONT 2 TEED 66kV Circuit | DH1 5FF | Replacement of 1.8km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | POTTER HOUSE - HIGH FLATTS 66kV Circuit | DH1 5FF | Replacement of 12.4km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | TEE TO HIGH FLATTS 66kV Circuit | DH2 2LR | Replacement of 7.7km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | TORONTO - EASTGATE CEMENT 2 (PART DUAL CIRCUIT) 66kV Circuit | DL14 7RJ | Replacement of 17.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor 275/132kV | DH6 5JY | 4 | 15 | 155000 | Toronto - Eastgate Cement 2 66kV Circuit | DL14 7RJ | Replacement of 12.3km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella North 275/132kV | NE15 8QF | 4 | 16 | 134000 | Bensham 66/11kV | NE8 2XY | Replacement of 11kV switchboard | Fault level | Q4 2025 | Q3 2026 | 30.5 | 30.5 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella North 275/132kV | NE15 8QF | 4 | 16 | 134000 | DUNSTON - RAVENSWORTH 2 TEED 66kV Circuit | NE11 9DH | Replacement of 8.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella North 275/132kV | NE15 8QF | 4 | 16 | 134000 | Dunston 66/20kV | NE11 9DH | Replacement of 20kV switchgear in a new switchroom | Condition | Q4 2024 | Q2 2025 | 30.3 | 30.3 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | Annfield 66/20kV | DH9 7XW | Replacement of 20kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | Annfield 66/20kV | DH9 7XW | Asset Replacement | Condition | Q2 2026 | Q3 2026 | 28 | 30 | 2
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | Birtley Grove 66/11kV | DH3 1JH | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | Coalburns 132/66kV | NE40 4JP | Asset replacement | Condition | Q1 2027 | Q3 2027 | 76.4 | 76.4 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | Team Valley 66/20kV | NE11 0SX | Replacement of 20kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Stella South 275/132kV | NE21 4FF | 4 | 9 | 91000 | West Wylam 66/20kV | NE42 5EX | Replacement of 20kV switchgear in a new switchroom | Condition | Q4 2023 | Q4 2024 | 30 | 30 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110000 | Gosforth Metro 1 33kV Circuit | NE3 1XL | Replacement of 0.1km of 33kV underground cables | Condition | Q1 2024 | Q3 2024 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110000 | Howdon 33/11kV | NE28 0JX | Replacement of 11kV switchgear in a new switchroom | Condition | Q4 2023 | Q3 2024 | 24 | 24 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110000 | Killingworth 33/11kV | NE12 6QQ | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110000 | PANDON - GOSFORTH 1 & 2 33kV Circuit | NE2 1XE | Replacement of 7.1km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110000 | Tee to Fossway 66kV Circuit | NE6 4AN | Replacement of 2.1km of 66kV underground cables | Condition | Q1 2024 | Q4 2024 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Boldon Downhill 66/20kV | NE36 0AS | Replacement of 20kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Carr Hill - West Boldon 1 & 2 66kV Circuit | NE10 9SY | Replacement of 7km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Carr Hill 66/11kV | NE10 9SY | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | HEBBURN - BENTON SQUARE TEED 66kV Circuit | NE31 1BD | Replacement of 1.6km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | HEBBURN - BENTON SQUARE TEED 66kV Circuit | NE31 1BD | Replacement of 1.3km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Hebburn 66/5.75kV | NE31 1BJ | Network rationalisation | Load | Q1 2026 | Q3 2027 | 12 | - | 15.4
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | High Barmston 66/11kV | NE38 8TE | Asset replacement | Condition | Q1 2028 | Q3 2028 | 20.1 | 40 | 19.9
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Leam Central - Hebburn West 66kV Circuit | NE10 8NQ | Replacement of 1.3km of 66kV underground cables | Condition | Q1 2024 | Q3 2024 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | TEMPLE PARK - WEST SOUTHWICK (PART DUAL CIRCUIT) 66kV Circuit | NE34 8TH | Replacement of 1.2km of 66kV underground cable | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Temple Park 66/11kV | NE34 8TG | Replacement of 66kV circuit breaker | Condition | Q3 2024 | Q3 2024 | 24 | 24 | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Usworth - West Boldon Teed 66kV Circuit | NE37 3HY | Replacement of 2.5km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148000 | Wardley 66/5.75kV | NE31 1UF | Network rationalisation | Load | Q1 2027 | Q3 2028 | 19 | - | 15.4
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Bolton Road 33/11kV | BD20 0JS | Replacement of transformer T1 and T2 | Condition | Q2 2025 | Q4 2025 | 15.3 | 30 | 14.7
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Bradford West 400/132kV | BD15 0BZ | Replacement of 132kV switchgear | Connections | Q4 2025 | Q4 2027 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | BRADFORD WEST-KEIGHLEY 132kV Circuit | BD13 2LX | Replacement of 0.7km of 132kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Chelker Reservoir 33/11kV | LS29 0JS | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Crosshills 33/11kV | BD20 7AH | Replacment of Transformers | Condition | Q1 2026 | Q3 2026 | 15.3 | 30 | 14.7
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Four Lane Ends 33/11kV | BD8 0LJ | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Furness Avenue 33/11kV | WF8 3JA | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Gaisby Lane 33/11kV | BD2 1BB | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Idle 33/11kV | BD10 8SA | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Ilkley 33/11kV | LS29 9BE | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Manchester Road 33/11kV | BD5 0QJ | Replacement of 11kV Switchgear | Condition | Q1 2024 | Q1 2025 | 23 | 23 | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | MENSTON 1-NORTH AVENUE 1 33kV Circuit | LS29 6BP | Replacement of 2.5km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Bradford West 275/132kV | BD15 0BZ | 8 | 42 | 263000 | Silsden 132/33kV | BD20 0LF | Replacement of 132/33kV transformers, 132kV switchgear and the 33kV switchgear | Load | Q1 2021 | Q4 2024 | 108 | 108 | 0
Yorkshire | North Yorkshire | Camblesforth 400/66kV | YO8 8HF | 1 | 5 | 19000 | Crowle 66/11kV | DN17 4BB | Installation of a 11kV interconnector | Load | 2029 | 2031 |  |  | 3
Yorkshire | North Yorkshire | Camblesforth 400/66kV | YO8 8HF | 1 | 5 | 19000 | Crowle 66/11kV | DN17 4BB | Flexibility | Load | 2024 | 2031 |  |  | 0.7
Yorkshire | North Yorkshire | Camblesforth 400/66kV | YO8 8HF | 1 | 5 | 19000 | Goole 66/11kV | DN14 6SX | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Beverley 132/33kV | HU17 0RW | Replacment of Transformer | Condition | Q4 2024 | Q3 2025 | 104 | 104 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Beverley 132/33kV | HU17 0RW | Replacement of 33kV switchboard | Connections | Q1 2025 | Q2 2026 | 104 | 104 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BEVERLEY 1-ENDIKE LANE 1 33kV Circuit | HU17 0RW | Replacement of 2.4km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BEVERLEY 1-FIGHAM HULL ROAD TEED 33kV Circuit | HU17 0RN | Replacement of 1.3km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BEVERLEY 1-SPARK MILL LANE 1 33kV Circuit | HU17 0RW | Replacement of 1.6km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BEVERLEY 2-EPPLEWORTH BOTT TEED 33kV Circuit | HU17 0RW | Replacement of 10.7km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BEVERLEY 2-SPARK MILL LANE 2 33kV Circuit | HU17 0RW | Replacement of 1.7km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | BRANSHOLME 1-TIVERTON ROAD 1 33kV Circuit | HU7 4ZN | Replacement of 2.2km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Burton Pidsea 66/11kV | HU12 9AE | Replacement of 66kV feeder Circuit Breakers | Condition | Q1 2024 | Q4 2024 | 9 | 9 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | CREYKE BECK 132KV Circuits | HU16 5SB | Replacement of 8.9km of 132kV underground cables | Connections | Q3 2024 | Q3 2026 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | DRIFFIELD 1-SEATON 1 66kV Circuit | YO25 5XR | Replacement of 11.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | DRIFFIELD 1-SEATON 1 66kV Circuit | YO25 5XR | Replacement of 15.2km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | DRIFFIELD 2-BRETT STREET 2 TEED 66kV Circuit | YO25 5XR | Replacement of 16.7km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Elgar Road 33/11kV | HU4 7JR | Replacement of 33kV and 11kV switchgear | Condition | Q1 2021 | Q2 2024 | 23 | 23 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Elgar Road 33/11kV | HU4 7NY | Replacement of 33kV Transformer T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Gibson Lane 33/11kV | HU14 3BQ | Replacement of 11kV switchboard | Connections | Q2 2025 | Q1 2026 | 23 | 23 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Gibson Lane 33/11kV | HU14 3HH | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Holme Upon Spalding Moor 33/11kV | YO43 4BX | Reinforcement | Load | Q2 2026 | Q3 2027 | 8 | 8 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Hull West 132/33kV | HU13 0JD | Replacement of 33kV switchboard | Connections | Q4 2027 | Q3 2028 | 117 | 117 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Hull West 132/33kV | HU13 0FA | Replace 132kV Transformer T1B&T2B | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | HUNMANBY 2 66kV Circuit | YO14 0JY | Replacement of 21.6km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Seaton 66/11kV | HU11 5RH | Replacement of 66kV Circuit Breakers | Condition | Q2 2025 | Q4 2025 | 20 | 20 | 0
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Southgate 33/11kV | YO43 3BE | Addition of a second 33/11kV transformer and 33kV ciruit, and 11kV switchboard extension | Load | Q2 2026 | Q3 2027 |  |  | 7.1
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Southgate 33/11kV | YO43 3BE | Flexibility | Load | 2024 | 2027 |  |  | 0.5
Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251000 | Spark Mill Lane 33/11kV | HU17 0TT | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | North Yorkshire | Drax 400/132kV | YO8 8PD | 2 | 4 | 25000 | RICCALL-WHITEMOOR 33kV Circuit | YO19 6QR | Replacement of 3km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Brighouse 132/33kV | HD6 1PZ | Replace 132kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | BRIGHOUSE 2-CLOUGH LSI 33kV Circuit | HD6 1QE | Replacement of 1.2km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Dowker Street 33/11kV | HD3 4JB | Replacement of 33kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Dowker Street 33/11kV | HD3 4JB | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Elland 33/11kV | HX5 9AE | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Hazlehead 33/11kV | HD9 7TT | Replacement of 11kV switchgear | Condition | Q3 2022 | Q3 2024 | 24 | 24 | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | LINDLEY 2-HARRISON LANE 33kV Circuit | HD3 3NY | Replacement of 8.6km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Millroyd Street 33/11kV | HD6 1JZ | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | Snelsins Lane 33/11kV | BD19 3UH | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | SOWERBY BRIDGE 3-MYTHOLMROYD 1 33kV Circuit | HX6 1EN | Replacement of 1.2km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | SOWERBY BRIDGE 4-HEBDEN BRIDGE 1 33kV Circuit | HX6 1EN | Replacement of 10km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Elland 275/132kV | HX5 9DN | 5 | 30 | 205000 | SOWERBY BRIDGE 4-MYTHOLMROYD 2 33kV Circuit | HX6 1EN | Replacement of 6.4km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60000 | FERRYBRIDGE A 1-BARLOW COMMON RD 66kV Circuit | WF11 8PR | Replacement of 16.8km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60000 | FERRYBRIDGE A 2-EGGBOROUGH TEED 66kV Circuit | WF11 8PR | Replacement of 23.3km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60000 | South Kirkby 66/11kV | WF9 3TJ | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | BRAMHAM 2-FENTON LANE 2 TEED 33kV Circuit | LS24 9NT | Replacement of 4km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | Featherstone 132/33kV | WF7 6HE | Replacement of 33kV switchboard | Connections | Q3 2026 | Q4 2028 | 117 | 117 | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | Kirkhaw Lane 132/33kV | WF11 8RD | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | KIRKHAW LANE 1-CARR LANE 1 33kV Circuit | WF11 8SB | Replacement of 1.9km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | Prince of Wales 33/11kV | WF8 4PR | Replacement of 33kV switchgear | Condition | Q1 2027 | Q3 2027 | 23 | 23 | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | Warren Lane 33/11kV | LS24 9NT | Replacement of 11kV Switchgear | Condition | Q1 2025 | Q3 2025 | 8 | 8 | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | Wetherby 33/11kV | TBC | Construction of new 33/11kV primary substation | Load | Q3 2026 | Q3 2027 | 0 | 30 | 30
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | WHINMOOR 2-BARWICK 2 33kV Circuit | LS14 2DG | Replacement of 6.3km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 1 | 8 | 60000 | WHINMOOR 2-BARWICK 2 33kV Circuit | LS14 2DG | Replacement of 1.7km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Barrow 33/11kV | DN19 7EG | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | BTP 33/11kV | DN31 2RL | Replacement of 33kV Transformer T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Convamore Road 33/11kV | DN32 9PG | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Conyard Road 33/11kV | DN35 8AJ | Replacement of transformer T1 and T2 | Condition | Q1 2026 | Q3 2026 | 23 | 24 | 1
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Doughty Road 33/11kV | DN32 0LR | Replacement of 33 kV incomer and 11 kV transformer tails | Load | 2024 | 2026 | 20.9 | 22.9 | 2
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Great Coates 33/11kV | DN37 9PN | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Grimsby Docks 33/6.6kV | DN40 2LZ | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Grimsby Docks 33/6kV | DN31 3TN | Replacement of Grimsby Docks PSS with a dedicated 11kV customer metering substation and Replacement of 33/11kV T1 at Marsden Road. | Condition | Q2 2025 | Q3 2025 | 23 | 0 | -23
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Humber Road 33/11kV | DN40 3LZ | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Humberston 132/33kV | DN36 4AW | Replace 132kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | HUMBERSTON 1-CONVAMORE ROAD 1 33kV Circuit | DN36 4AW | Replacement of 1.8km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | IMMINGHAM 1-MILLENIUM INORGAN 1 33kV Circuit | DN40 1QT | Replacement of 2.4km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Netherlands Way 132/33kV | DN41 8DF | Construction of new 132/33kV supply point | Connections | 2024 | 2027 | 0 | 120 | 120
Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85000 | Scartho 33/11kV | DN33 3JL | Replacement of 33kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Blyton 132/33kV | DN21 3NS | Replace 132kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | BLYTON 2-HAXEY 33kV Circuit | DN21 3NS | Replacement of 5.1km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | BLYTON 2-HAXEY 33kV Circuit | DN21 3NS | Replacement of 5km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Bottesford 33/11kV | DN16 3UJ | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Bridges Road 33/11kV | DN17 1HA | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Corringham Road 33/11kV | DN21 1FF | Replacement of 11kV switchgear in a new switchroom. | Condition | Q4 2024 | Q3 2025 | 23 | 23 | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Corringham Road 33/11kV | DN21 1FT | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Epworth 33/11kV | DN9 1JU | Green recovery reinforcement | Load | 2022 | 2025 | 10 | 24 | 14
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Foxhills 33/11kV | DN15 8QN | Replacement of Switchgear | Fault level | Q1 2027 | Q3 2027 | 18 | 18 | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Grainthorpe 33/11kV | LN11 7JU | Replacement of 33kV Transformers | Condition | Q1 2027 | Q3 2027 | 7.5 | 8 | 0.5
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Hibaldstow 33/11kV | DN21 4NJ | Replacement of 11kV Switchgear | Condition | Q2 2028 | Q4 2028 | 15.3 | 15.3 | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Hibaldstow 33/11kV | DN21 4NH | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Keadby - Santon Tee 1 & 2 132kV Circuit | DN17 3EW | Replacement of 12km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Keadby 400/132kV | DN17 3EL | Total overhaul of GSP | Connections | Q2 2025 | Q3 2031 |  |  | GSP* (*We are not reporting changes to Natianal Grid capacity)
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | KEADBY-SCAWBY BROOK 132kV Circuit | DN17 3EW | Replacement of 1.8km of 132kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Normanby 33/11kV | LN8 2HQ | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124000 | Scunthorpe South 132/33kV | DN16 1BD | Replace 132kV Transformer T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127000 | Iveson House 33/11kV | LS16 6RF | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127000 | Morley 33/11kV | LS27 9HS | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127000 | WHINGATE 2-FARNLEY CRESCENT 2 33kV Circuit | LS12 3QT | Replacement of 1.9km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127000 | Whingate 33/11kV | LS12 3QT | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127000 | Whitehall Road 33/11kV | LS1 4EE | Replacement of 11kV switchgear | Condition | Q1 2024 | Q2 2025 | 19 | 19 | 0
Yorkshire | South Yorkshire and North Linconshire | Neepsend 275/33kV | S6 2FH | 1 | 7 | 55000 | BEELEY WOOD-LOXLEY ROAD 33kV Circuit | S6 1ND | Replacement of 3.5km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Neepsend 275/33kV | S6 2FH | 1 | 7 | 55000 | Blue Boy Street 33/11kV | S3 7BA | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Neepsend 275/33kV | S6 2FH | 1 | 7 | 55000 | Claywheels Lane 33/11kV | S6 1LY | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Neepsend 275/33kV | S6 2FH | 1 | 7 | 55000 | Neepsend 275/33kV | S6 2FH | Replacement of 6.3km of 33kV underground cables | Condition | Q2 2023 | Q3 2024 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Marmion Road 33/11kV | S11 8TS | Asset replacement | Condition | Q3 2027 | Q4 2028 | 24 | 30 | 6
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Marmion Road 33/11kV | S11 8TS | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Marmion Road 33/11kV | S11 8TS | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Marmion Road 33/11kV | S11 8TS | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Saxon Road 33/11kV | S8 0XQ | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Norton Lees 275/33kV | S8 9BH | 1 | 5 | 54000 | Saxon Road 33/11kV | S8 0XQ | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Pitsmoor 3/4 275/33kV | S4 8LU | 1 | 5 | 24000 | Newhall Road 33/11kV | S9 2RS | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Pitsmoor 3/4 275/33kV | S4 8LU | 1 | 5 | 24000 | Pitsmoor 275/33kV | S4 8LU | Replacement of 33kV switchgear | Condition | Q2 2024 | Q4 2026 |  |  | 0
Yorkshire | Humber | Saltend North 275/132kV | HU12 8EY | 3 | 10 | 33000 | Hedon Road 33/11kV | HU12 8ED | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | Humber | Saltend North 275/132kV | HU12 8EY | 3 | 10 | 33000 | Hull East 132/33kV | HU9 5NP | Asset replacement | Condition | Q1 2027 | Q3 2027 | 117 | 156 | 39
Yorkshire | Humber | Saltend North 275/132kV | HU12 8EY | 3 | 10 | 33000 | Hull East 33/11kV | HU9 5NP | Replacement of 11kV switchgear in a new switchroom. | Condition | Q1 2024 | Q4 2024 | 23 | 23 | 0
Yorkshire | Humber | Saltend North 275/132kV | HU12 8EY | 3 | 10 | 33000 | Saltend 132/33kV | HU12 8EY | Replacement of 33kV switchboard and Tx1 | Connections | Q1 2028 | Q4 2028 | 50.8 | 117 | 66.2
Yorkshire | Humber | Saltend North 275/132kV | HU12 8EY | 3 | 10 | 33000 | Withernsea 33/11kV | HU19 2LD | Replacement of 11kV switchgear | Condition | Q4 2023 | Q2 2024 | 10 | 10 | 0
Yorkshire | South Yorkshire and North Linconshire | Sheffield City 275/33kV | S3 7WR | 1 | 7 | 31000 | Arundel Street 33/11kV | S1 4PJ | Replacement of 11kV Switchgear | Condition | Q2 2025 | Q2 2026 | 24 | 24 | 0
Yorkshire | South Yorkshire and North Linconshire | Sheffield City 275/33kV | S3 7WR | 1 | 7 | 31000 | Ellin Street 33/11kV | S1 4QZ | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Sheffield City 275/33kV | S3 7WR | 1 | 7 | 31000 | Victoria Street 33/11kV | S3 7QB | Replacement of 11kV switchgear | Condition | Q4 2024 | Q4 2026 | 24 | 24 | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Clarence Road 33/11kV | LS10 1JE | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Dalton 33/11kV | HD2 1FF | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Folly Hall 33/11kV | HD1 3PL | Replacement of 11kV circuit breakers | Condition | Q2 2025 | Q1 2026 | 24 | 24 | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Folly Hall 33/11kV | HD1 3TF | Replacement of 33kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Folly Hall 33/11kV | HD1 3TF | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Hillcrest 33/11kV | LS8 3AA | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | LEEDS EAST 3-HILLCREST 1 33kV Circuit | LS9 6ED | Replacement of 2.3km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | LEEDS EAST 4-HILLCREST 2 33kV Circuit | LS9 6ED | Replacement of 2.3km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Low Moor 33/11kV | BD12 0NG | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | LOW ROAD 3-LEASOWE ROAD 1 33kV Circuit | LS10 1RH | Replacement of 1.2km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | LOW ROAD 3-LEASOWE ROAD 2 33kV Circuit | LS10 1RH | Replacement of 1.2km of 33kV underground cable | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Selby Road 33/11kV | LS15 0QE | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Skelton Grange - Rodley 1 & 2 132kV Circuit | LS9 0PJ | Replacement of 22.3km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Skelton Grange -Rodley 132kV Circuit | LS9 0PJ | Replacement of 22.3km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Spring Mill Street 33/11kV | BD5 7DT | Replacement of 11kV Switchgear | Condition | Q4 2024 | Q4 2025 | 23 | 23 | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | STAYGATE 1-TONG STREET 1 33kV Circuit | BD6 1YA | Replacement of 1.3km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Staygate Odsal 1 & 2 33kV Circuit | BD6 1YA | Replacement of 1.4km of 33kV underground cables | Condition | Q1 2024 | Q4 2024 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Staygate Tee 1 & 2 132kV Circuit | BD6 1YA | Replacement of 4.5km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Swinnow Moor 33/11kV | LS13 4RJ | Replacment of Transformers | Condition | Q1 2026 | Q3 2026 | 23 | 30 | 7
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | Thornbury 33/11kV | BD3 7AD | Replacement of 11kV switchgear and transformers | Condition | Q3 2025 | Q2 2026 | 23 | 30 | 7
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | WAKEFIELD MO R 1-DURKAR LOW LN 1 33kV Circuit | WF1 3HS | Replacement of 1.3km of 33kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | White Lee 33/11kV | WF16 9QA | Replacement of 11kV Switchgear | Condition | Q4 2023 | Q1 2026 | 23 | 23 | 0
Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312000 | York Road 33/11kV | LS9 6TF | Replacement of 33kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | BEIGTHON 1-HACKENTHORPE 2 66kV Circuit | S26 4TL | Replacement of 4.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | Edlington 66/11kV | DN12 1SU | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | Edlington 66/11kV | DN12 1SU | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | EDLINGTON-BALBY 2 66kV Circuit | DN12 1SU | Replacement of 2km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | Hackenthorpe 66/11kV | S12 4ET | Replacement of 66kV switchgear and 11kV switchgear | Condition | Q1 2021 | Q2 2024 | 24 | 24 | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | Kiveton Park 66/11kV | S26 6RP | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | New Orchard Lane 66/11kV | S66 9EP | Replacement of Tx 1 | Connections | Q1 2027 | Q3 2027 | 23 | 23 | 0
Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100000 | TICKHILL ROAD 2-DINNINGTON 1 66kV Circuit | S66 7QN | Replacement of 7.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | ARMTHORPE-MARKHAM GATES 66kV Circuit | DN3 3DY | Replacement of 3.6km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Askern 66/11kV | DN6 0BY | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Attercliffe 132/33kV | S9 3FA | Replacment of Transformers | Condition | Q1 2026 | Q3 2026 | 69 | 117 | 48
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Balby 66/11kV | DN4 8DG | Replacement of 66kV Transformer T1 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Barnburgh 66/11kV | S63 9NT | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Blackburn Meadows 33/11kV | S9 1HF | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Brodsworth 66/11kV | DN5 7XB | Replacement of 66kV Transformer T1&T2 | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Brodsworth 66/11kV | DN5 7XB | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | DONCASTER B 1-ROCKWARE 1 66kV Circuit | DN5 8UX | Replacement of 5km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | HICKLETON 1-BRODSWORTH 2 66kV Circuit | S63 0DE | Replacement of 7.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Hickleton 66/11kV | S63 0DE | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Hickleton 66/11kV | S63 0DE | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Kirk Sandall 66/11kV | DN3 1HR | Replacement of 66kV Circuit Breakers | Condition | Q3 2024 | Q1 2025 | 24 | 24 | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Stainforth 66/11kV | DN7 5HD | Relocate the substation to a new suitable site and install new plant. | Condition | Q1 2024 | Q4 2025 | 23 | 24 | 1
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | THORPE MARSH 5-STAINFORTH 1 TEED 66kV Circuit | DN5 8UX | Replacement of 12.1km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Wheatley Park 66/11kV | DN2 4HG | Replacement of both 66/11kV Transformers, 66kV circuit breakers and the 11kV switchgear | Condition | Q1 2024 | Q3 2025 | 23 | 23 | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Durkar Low Lane 33/11kV | WF2 7GP | Replacement of 11kV switchgear in a new switchroom. | Condition | Q4 2023 | Q3 2024 | 24 | 24 | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Ecclesfield 66/11kV | S35 9TG | Replacement of 66kV Circuit Breakers and 11kV switchgear | Condition | Q4 2025 | Q4 2026 | 23 | 23 | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192000 | Elsecar 66/11kV | S74 8HW | Replacement of 66/11kV transformer T1, 66kV circuit breaker and 11kV switchgear | Condition | Q3 2026 | Q4 2027 | 23 | 24 | 1
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | HOUGHTON MAIN-DEARNE ROAD 66kV Circuit | S72 0GX | Replacement of 4.8km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Hunningley Tee 1 & 2 132kV Circuit | S70 3ET | Replacement of 3.5km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Scissett 66/11kV | HD8 9LS | Replacement of the 66kV circuit breaker | Condition | Q3 2024 | Q4 2025 | 23 | 23 | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Tankersley Park 66/11kV | S35 2PT | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | TANKERSLEY PARK 66kV Circuit | S35 2PT | Replacement of 4.2km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | West Melton - Hunshelf 1 & 2 132kV Circuit | S63 6EZ | Replacement of 17.5km of 132kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | WEST MELTON 2-ECCLESFIELD 2 66kV Circuit | S63 6EZ | Replacement of 10km of 66kV overhead line | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Wheatacre Road 66/11kV | S36 2GQ | Addition of a second 66/11kV transformer and 11kV switchboard extension | Load | 2029 | 2031 |  |  | 4.8
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Wheatacre Road 66/11kV | S36 2GQ | Flexibility | Load | 2024 | 2031 |  |  | 1.3
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Woolley 66/11kV | S75 5JE | Replacement of 66kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Woolley 66/11kV | S75 5JE | Replacement of 11kV switchgear | Condition | 2029 | 2033 |  |  | 0
Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189000 | Worsborough Park 66/11kV | S70 5LY | Replacement of 66kV Circuit Breakers and 11kV switchgear | Condition | Q3 2024 | Q3 2025 | 23 | 23 | 0

## Table 2
Scheme Status | Licence Area | Northern Powergrid Operational Region | Grid Supply Point | GSP Postcode | Number of BSPs at GSP | Number of Primary Substations at GSP | Number of Customers at GSP | Upcoming Flexibility Needs Substation | Substation Postcode | Postal Sectors Supplied from Substation | Driver | Flexibility Needs Start Year
Signposted | Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192k | Armthorpe 66/11kV | DN3 3DY | DN3 2; DN3 3; DN7 4; DN7 6; DN8 5; | Load | 2030
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Audby Lane 33/11kV | LS22 7SU | HG3 1; HG5 8; LS22 4; LS22 5; LS22 6; LS22 7; LS23 6; LS23 7; LS24 8; YO26 7; YO26 8; YO5 8 | Load | 2033
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Beverley 132/33kV | HU17 0RW | HU16 4; HU16 5; HU5 2; HU5 4; HU6 7; HU6 8; HU6 9; HU5 2; HU6 7; HU6 8; HU6 9; HU7 0; HU7 6; HU8 0; DN14 7; HU15 2; YO42 1; YO42 4; YO43 3; YO43 4; YO62 5; YO8 6; YO8 7; HU17 0; HU17 5; HU17 7; HU17 8; HU17 9; YO25 3; YO25 9; YO43 4; HU15 2; HU17 7; YO25 9; YO42 4; YO4 3; YO43 3; YO43 4; DN18 5; HU10 6; HU10 7; HU13 0; HU14 3; HU15 1; HU16 4; HU16 5; HU17 8; HU20 3; HU5 5; HU16 4; HU17 0; HU17 7; HU17 8; HU17 9; HU6 0; HU6 7; YO25 9; | Load | 2029
Signposted | Yorkshire | West Yorkshire | Kirkstall B 275/132kV | LS12 2QX | 4 | 18 | 127k | Bramley 33/11kV | LS13 3ST | LS12 2; LS12 3; LS13 1; LS13 2; LS13 3; LS13 4 | Load | 2032
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Brett Street 66/11kV | YO16 4HW | YO15 2; YO15 3; YO16 4; YO16 6; YO16 7; YO25 0; YO25 4; YO25 5; YO25 8 | Load | 2032
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Bridges Road 33/11kV | DN17 1HA | DN15 7; DN15 8; DN16 2; DN16 3; DN17 1; DN17 2; DN17 3 | Load | 2033
Signposted | Yorkshire | South Yorkshire and North Linconshire | Neepsend 275/33kV | S6 2FH | 1 | 7 | 55k | Claywheels Lane 33/11kV | S6 1LY | S30 3; S35 0; S35 8; S5 8; S5 9; S6 1; S6 2; S6 4; S6 6 | Load | 2028
Signposted | Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85k | Clough Lane 33/11kV | DN40 3EH | DN19 7; DN39 6; DN40 3 | Load | 2031
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Commonside Lane 33/11kV | WF7 5DF | WF2 7; WF4 1; WF6 1; WF6 4; WF7 5; WF7 6; WF7 7; WF8 4 | Load | 2030
Signposted | Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100k | Costhorpe 66/11kV | S81 9QR | DN10 6; DN11 8; DN22 8; S80 2; S81 0; S81 8; S81 9 | Load | 2031
Signposted | Northeast | Teeside | Norton GSP 275/132kV | TS21 1EG | 10 | 34 | 246k | Darlington West 33/11kV | DL3 9QG | DL1 1; DL2 2; DL3 0; DL3 6; DL3 7; DL3 8; DL3 9 | Load | 2033
Signposted | Yorkshire | South Yorkshire and North Linconshire | West Melton / Thorpe Marsh 275/132kV | S63 6LS | 9 | 34 | 192k | Doncaster B/Thorpe Marsh 132/66kV | DN5 8UX | DN3 2; DN3 3; DN7 4; DN7 6; DN8 5; DN14 0; DN5 0; DN6 0; DN6 8; DN6 9; WF8 2; WF8 3; DN10 6; DN11 0; DN11 8; DN11 9; DN4 5; DN4 6; DN4 7; DN4 8; DN5 7; S63 0; S63 8; S63 9; S73 9; DN12 3; DN4 5; DN5 7; DN5 8; DN6 0; DN6 7; DN6 8; S63 7; DN5 7; S63 0; S63 9; DN1 2; DN2 4; DN2 5; DN5 9; DN2 4; DN2 5; DN3 1; DN3 2; DN3 3; DN7 4; DN2 5; DN2 6; DN3 2; DN3 3; DN4 5; DN4 6; DN4 7; DN20 8; DN2 4; DN2 5; DN3 1; DN3 2; DN3 1; DN6 0; DN7 4; DN7 5; DN7 6; DN8 5; DN10 6; DN14 0; DN14 4; DN14 8; DN14 9; DN17 4; DN6 0; DN7 5; DN7 6; DN8 4; DN8 5; DN85 4; DN11 0; DN11 9; DN3 3; DN4 6; DN4 7; DN4 8; DN9 3; DN3 3; DN9 3; DN1 1; DN1 2; DN2 4; DN2 5; DN2 6; | Load | 2028
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Driffield 66/11kV | YO25 5XR | HD8 0; YO25 0; YO25 3; YO25 4; YO25 5; YO25 6; YO25 7; YO25 8; YO25 9 | Load | 2033
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Dunkeswick 33/11kV | LS17 9LP | HG3 1; HG5 8; LS16 8; LS16 9; LS17 0; LS17 7; LS17 9; LS21 1; LS22 4; LS22 6; YO41 5 | Load | 2029
Signposted | Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85k | Eastfield Road 33/11kV | DN40 3LW | DN37 8; DN39 6; DN40 1; DN40 2; DN40 3; DN41 8 | Load | 2030
Signposted | Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60k | Eggborough 66/11kV | DN14 0QA | DN14 0; LN12 1; WF11 8; YO8 8 | Load | 2032
Signposted | Northeast | Teeside | Norton GSP 275/132kV | TS21 1EG | 10 | 34 | 246k | Faraday Street 66/11kV | TS1 4JG | TS1 2; TS1 3; TS1 4; TS1 5; TS17 7; TS2 1; TS3 7; TS4 2; TS5 4; TS5 5; TS5 6 | Load | 2028
Signposted | Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60k | Ferrybridge A 66/11kV | WF11 8RR | LS25 5; WF10 2; WF10 3; WF11 0; WF11 8; WF11 9; WF8 1; WF8 2; YO8 9 | Load | 2029
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Gibson Lane 33/11kV | HU14 3HH | HU10 7; HU1 2; HU13 0; HU14 3; HU15 1; HU2 0 | Load | 2033
Signposted | Northeast | Teeside | Lackenby 275/66kV | TS6 7QR | 1 | 6 | 99k | Grangetown 66/11kV | TS6 7AS | TS10 4; TS10 5; TS1 1; TS11 8; TS14 6; TS3 6; TS6 0; TS6 6; TS6 7; TS6 8; TS6 9; TS7 0; TS9 6 | Load | 2033
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Harpswell 33/11kV | DN21 5UT | DN20 9; DN21 3; DN21 4; DN21 5; LN1 2; LN1 3; LN8 2; LN8 3 | Load | 2032
Signposted | Northeast | Northumberland, County Durham and Tyne & Wear | Hawthorn Pit Grid 275/66kV | DH6 2TX | 1 | 6 | 70k | Hawthorn Pit 66/20kV | SR7 9NX | DH4 4; DH5 0; DH5 8; DH5 9; DH6 1; DH6 2; DH6 3; SR2 0; SR3 2; SR7 0; SR7 7; SR7 8; SR7 9; SR8 3 | Load | 2029
Signposted | Northeast | North Yorkshire | Osbaldwick 400/132kV | YO10 3WA | 6 | 23 | 161k | Haxby Road T2 T3 33/11kV | YO31 8FZ | YO30 6; YO30 7; YO31 8; YO31 9; YO32 2; YO32 3; YO32 4; YO32 9 | Load | 2032
Signposted | Yorkshire | West Yorkshire | Ferrybridge A 275/66kV | WF11 8PR | 1 | 8 | 60k | Hemsworth 66/11kV | WF9 5BZ | WF4 1; WF4 2; WF7 7; WF8 3; WF9 1; WF9 4; WF9 5 | Load | 2029
Signposted | Northeast | Northumberland, County Durham and Tyne & Wear | West Boldon 275/66kV | NE36 0BG | 1 | 18 | 148k | High Barmston 66/11kV | NE38 8QA | DH4 7; NE37 2; NE37 3; NE38 7; NE38 8; NE38 9; SR4 9; SR5 3 | Load | 2030
Signposted | Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82k | Husthwaite 33/11kV | YO61 4PN | DL6 3; TS9 7; YO51 9; YO60 6; YO61 1; YO61 2; YO61 3; YO61 4; YO61 5; YO62 4; YO62 5; YO6 3; YO7 2; YO7 3 | Load | 2029
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Keddington Road 33/11kV | LN11 0DE | LN11 0; LN11 7; LN11 8; LN11 9; LN12 1 | Load | 2033
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Kirkburn 66/11kV | YO25 9EH | YO17 9; YO25 0; YO25 1; YO25 3; YO25 4; YO25 8; YO25 9; YO42 1 | Load | 2025
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Leeds Road 33/11kV | LS22 5AA | LS14 1; LS14 3; LS17 9; LS22 4; LS22 5; LS23 6 | Load | 2032
Signposted | Northeast | Northumberland, County Durham and Tyne & Wear | Blyth 275/132kV | NE22 7BF | 2 | 4 | 33k | Linton 66/20kV | NE61 3AX | NE61 3; NE61 4; NE61 5; NE61 6; NE65 0; NE65 8; NE65 9 | Load | 2032
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Martongate 66/11kV | YO16 6RX | YO14 0; YO14 9; YO15 1; YO15 2; YO16 4; YO16 6; YO16 7 | Load | 2030
Signposted | Northeast | Northumberland, County Durham and Tyne & Wear | Tynemouth 275/132kV | NE27 0QG | 4 | 10 | 110k | Monkseaton 33/11kV | NE25 9AF | NE25 0; NE25 8; NE25 9; NE26 1; NE26 2; NE26 3; NE26 4; NE27 0; NE29 8 | Load | 2028
Signposted | Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312k | Moor Road 33/11kV | LS6 4BJ | LS16 5; LS16 7; LS16 8; LS4 2; LS5 3; LS6 1; LS6 2; LS6 3; LS6 4 | Load | 2028
Signposted | Yorkshire | South Yorkshire and North Linconshire | Thurcroft 275/66kV | S66 9JD | 1 | 11 | 100k | New Orchard Lane 66/11kV | S66 9HY | S25 1; S25 7; S26 3; S60 4; S66 1; S66 8; S66 9 | Load | 2030
Signposted | Northeast | Teeside | Norton GSP 275/132kV | TS21 1EG | 10 | 34 | 246k | Norton GSP 275/132kV | TS21 1EG | DL1 3; DL2 1; TS16 0; TS18 1; TS18 2; TS18 3; TS18 4; TS18 5; TS19 0; TS19 7; TS19 8; TS19 9; TS20 1; TS20 2; TS21 1; TS21 3; TS22 5 | Load | 2029
Signposted | Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312k | Rodley Lane 33/11kV | LS13 1LJ | BD10 0; LS13 1; LS18 4; LS18 5; LS19 6; LS28 5; LS28 8; LS5 3 | Load | 2031
Signposted | Yorkshire | West Yorkshire | Skelton Grange 275/132kV | LS10 1RS | 11 | 46 | 312k | Saint Andrews Road 132/33kV | HD1 6SE | HD1 4; HD1 5; HD1 6; HD2 1; HD2 2; HD3 3; HD1 2; HD1 6; HD4 6; HD5 0; HD5 8; HD5 9; HD8 0; HD1 1; HD1 2; HD1 3; HD1 4; HD1 6; HD4 6; HD5 8; HD5 9; HD1 1; HD1 2; HD1 3; HD1 4; HD1 5; HD1 6; HD2 2; HD5 0; HD5 8; HD5 9; HD1 3; HD1 4; HD4 5; HD4 6; HD4 7; HD7 1; | Load | 2032
Signposted | Yorkshire | Humber | Grimsby West 400/132kV | DN37 9PE | 5 | 15 | 85k | Scartho 33/11kV | DN33 3JL | DN32 0; DN32 9; DN33 1; DN33 2; DN33 3; DN34 5; DN36 4; DN36 5; DN37 0; DN37 7; DN37 9; LN7 6 | Load | 2031
Signposted | Yorkshire | Humber | Creyke Beck 400/132kV | HU16 5SB | 8 | 36 | 251k | Seaton 66/11kV | HU11 5RQ | HU11 4; HU11 5; HU17 5; HU18 1; HU19 2; HU6 9; HU8 9; YO25 8 | Load | 2033
Signposted | Yorkshire | North Yorkshire | Drax 400/132kV | YO8 8PD | 2 | 4 | 25k | Selby 33/11kV | YO8 8NB | LN8 3; LS24 9; YO19 6; YO8 0; YO8 3; YO8 4; YO8 5; YO8 6; YO8 8; YO8 9 | Load | 2029
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Sherburn 33/11kV | LS25 6PL | LS24 9; LS25 5; LS25 6; YO8 3 | Load | 2032
Signposted | Northeast | Northumberland, County Durham and Tyne & Wear | Spennymoor GSP 275/132kV | DH6 5JY | 4 | 15 | 155k | Spennymoor 66/20kV | DH6 5JX | DH1 2; DH1 3; DH2 3; DH6 4; DH6 5; DH7 8; DL14 1; DL14 7; DL14 8; DL16 6; DL16 7; DL17 0; DL17 8; DL17 9; DL4 2 | Load | 2032
Signposted | Northeast | North Yorkshire | Knaresborough 275/132kV | HG5 9JQ | 5 | 13 | 82k | Starbeck 33/11kV | HG2 7PT | HG1 3; HG1 4; HG2 7; HG2 8; HG3 1; HG3 3; HG5 0; HG5 8; HG5 9 | Load | 2026
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Station Road 33/11kV | DN15 6BT | DN15 0; DN15 6; DN15 7; DN15 8; DN16 1; DN16 2; DN16 3; DN17 1 | Load | 2032
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Stow 33/11kV | LN1 2AJ | DN21 4; DN21 5; LN1 2; LN2 2 | Load | 2029
Signposted | Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189k | Tankersley Park 66/11kV | S35 2PT | S30 4; S30 7; S35 1; S35 2; S35 3; S35 4; S35 7; S60 4; S61 2; S62 7; S70 5; S74 0; S75 3; | Load | 2031
Signposted | Northeast | Teeside | Norton GSP 275/132kV | TS21 1EG | 10 | 34 | 246k | Thirsk 33/11kV | YO7 4NH | DL6 3; DL7 9; DL8 2; YO61 2; YO7 1; YO7 2; YO7 3; YO7 4 | Load | 2031
Signposted | Yorkshire | South Yorkshire and North Linconshire | Keadby 400/132kV | DN17 3EL | 6 | 27 | 124k | Walesby 33/11kV | LN8 3UL | LN1 2; LN3 5; LN7 6; LN8 3; LN8 5; LN8 6 | Load | 2031
Signposted | Yorkshire | West Yorkshire | Ferrybridge B 275/132kV | WF11 8PR | 7 | 23 | 137k | Wellington Street 33/11kV | WF10 1NW | LS26 9; WF10 1; WF10 4; WF10 5; WF6 1; WF6 2; WF7 5; WF7 6 | Load | 2032
Signposted | Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189k | West Melton 132/66kV | S63 6EZ | S63 6; S70 3; S71 5; S73 0; S73 8; S73 9; S74 0; S74 9; S63 5; S63 6; S63 7; S71 1; S73 0; S30 3; S30 4; S30 9; S35 1; S35 8; S35 9; S38; S59; S61 2; S60 4; S62 7; S63 6; S73 0; S74 0; S74 8; S74 9; S63 0; S70 1; S71 5; S72 0; S72 7; S73 0; S73 9; S62 5; S62 6; S62 7; S64 5; S64 8; S30 4; S30 7; S35 1; S35 2; S35 3; S35 4; S35 7; S60 4; S61 2; S62 7; S70 5; S74 0; S75 3; S63 5; S63 6; S63 7; S63 8; S63 9; S64 0; S64 9; S72 0; S63 5; S70 4; S70 5; S70 6; S74 0; S74 8; S74 9; S75 3; | Load | 2031
Signposted | Yorkshire | South Yorkshire and North Linconshire | West Melton Section 3 275/132kV | S63 6LS | 5 | 26 | 189k | Wheatacre Road 66/11kV | S36 2GQ | S30 5; S35 0; S35 7; S36 1; S36 2; S36 3; S36 4; S36 9; S66 | Load | 2023